## Members & Roles + Objectives +
Project — ALS1
Team: Ferran · Luz · Noa · Leyre ¦ Course: Introduction to Bioinformatics 2026–2027
Molecular Analysis of SOD1 Gene Mutations in Amyotrophic Lateral Sclerosis 1 (ALS1)
Project Name:
General Objective: explain the impact of changes in genetic and protein sequences on the

## Gantt
Gantt chart — ALS1
Team: Ferran · Luz · Noa · Leyre ¦ Course: Introduction to Bioinformatics 2026–2027 ¦ Live version
Progress (subtasks completed): |  | 2.632% | Status updated up to: |  |  |  | 2026-10-08
ID | Task | Owner | Plan. start | Plan. end | Real start | Real end | Days | Predecessor | Status | September 2026 | [9 empty] | October 2026 | [21 empty] | November 2026
[10 empty] | 14/09 |  | 21/09 |  |  |  |  | 28/09 |  |  |  |  | 05/10 |  |  |  |  | 12/10 |  |  |  |  | 19/10 |  |  |  |  | 26/10 |  |  |  |  | 02/11
[10 empty] | 2026-09-17 | 2026-09-18 | 2026-09-21 | 2026-09-22 | 2026-09-23 | 2026-09-24 | 2026-09-25 | 2026-09-28 | 2026-09-29 | 2026-09-30 | 2026-10-01 | 2026-10-02 | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-11-02 | 2026-11-03 | 2026-11-04 | 2026-11-05
1 | Project management & setup |  | 2026-09-17 | 2026-10-26 |  |  | 26
1.1 | GitHub environment setup |  | 2026-09-17 | 2026-10-09 |  |  | 16
1.1.1 | Setting up repository | Noa & Ferran | 2026-09-17 | 2026-09-17 | 2026-09-17 | 2026-09-17 | 1 |  | Completed
1.1.2 | Repository update to Formal Requirements (name, report/, references/, README) | Leyre | 2026-10-09 | 2026-10-09 |  |  | 1 | 1.1.1 | Pending
1.2 | Project planning |  | 2026-10-01 | 2026-10-09 |  |  | 7
1.2.1 | Gantt chart (Excel) | All | 2026-10-01 | 2026-10-08 | 2026-09-29 |  | 6 | 1.1.1 | In progress
1.2.2 | Risk assessment | Leyre | 2026-10-05 | 2026-10-08 | 2026-10-06 |  | 4 | 1.2.1 (SS) | In progress
1.2.3 | Gantt v1 export to PDF, Moodle submission and freeze in repo | Luz | 2026-10-09 | 2026-10-09 |  |  | 1 | 1.2.1, 1.2.2 | Pending
1.3 | Literature review |  | 2026-10-06 | 2026-10-22 |  |  | 12
1.3.1 | Bibliography selection | All | 2026-10-06 | 2026-10-09 | 2026-10-06 |  | 4 |  | In progress
1.3.2 | Extraction of information and storage of sources | All | 2026-10-13 | 2026-10-21 |  |  | 7 | 1.3.1 | Pending
1.3.3 | In-text citations and reference list (Oxford SCIMED) | All | 2026-10-15 | 2026-10-22 |  |  | 6 | 1.3.1 | Pending
1.4 | Project monitoring |  | 2026-10-09 | 2026-10-26 |  |  | 11
1.4.1 | Project Status and live Gantt updates (Mon & Thu) | Ferran | 2026-10-09 | 2026-10-26 |  |  | 11 | 1.2.1 | Pending
1.4.2 | Risk monitoring | Leyre | 2026-10-09 | 2026-10-26 |  |  | 11 | 1.2.2 | Pending
1.4.3 | Retrospective preparation | Ferran | 2026-10-21 | 2026-10-21 |  |  | 1 | 1.4.1 (SS) | Pending
2 | Bioinformatic analysis |  | 2026-10-13 | 2026-10-20 |  |  | 6
2.1 | Sequence, mutation and structure analysis |  | 2026-10-13 | 2026-10-16 |  |  | 4
2.1.1 | Disease cause at gene, protein, structure and function level | Luz | 2026-10-13 | 2026-10-14 |  |  | 2 | 1.3.1 | Pending
2.1.2 | Variant selection and numbering mapping table | Leyre | 2026-10-13 | 2026-10-14 |  |  | 2 | 1.3.1 | Pending
2.1.3 | Wild-type vs mutant sequence alignment | Leyre | 2026-10-15 | 2026-10-16 |  |  | 2 | 2.1.2 | Pending
2.1.4 | Mapping of variants onto the 3D structure | Ferran | 2026-10-15 | 2026-10-16 |  |  | 2 | 2.1.2 | Pending
2.2 | Evolutionary conservation |  | 2026-10-13 | 2026-10-19 |  |  | 5
2.2.1 | Species selection (≥ 2) and ortholog retrieval | Noa | 2026-10-13 | 2026-10-14 |  |  | 2 | 1.3.1 | Pending
2.2.2 | Multiple sequence alignment and conservation of mutated residues | Noa | 2026-10-15 | 2026-10-16 |  |  | 2 | 2.1.2, 2.2.1 | Pending
2.2.3 | Selective pressure in evolution | Noa | 2026-10-19 | 2026-10-19 |  |  | 1 | 2.2.2 | Pending
2.3 | Structure–function impact |  | 2026-10-19 | 2026-10-20 |  |  | 2
2.3.1 | Healthy vs disease differences at gene, protein, structure and function level | Ferran | 2026-10-19 | 2026-10-19 |  |  | 1 | 2.1.1, 2.1.3, 2.1.4 | Pending
2.3.2 | Impact on patient function | Luz | 2026-10-20 | 2026-10-20 |  |  | 1 | 2.3.1 | Pending
3 | Report writing (BMC Bioinformatics format) |  | 2026-10-13 | 2026-10-23 |  |  | 9
3.1 | Background and Methods |  | 2026-10-13 | 2026-10-21 |  |  | 7
3.1.1 | Report skeleton (BMC sections) and figure plan | Ferran | 2026-10-13 | 2026-10-13 |  |  | 1 | 1.1.2 | Pending
3.1.2 | Background | Luz | 2026-10-15 | 2026-10-16 |  |  | 2 | 2.1.1, 3.1.1 | Pending
3.1.3 | Methods | Leyre | 2026-10-21 | 2026-10-21 |  |  | 1 | 2.1.3, 2.1.4, 2.2.2 | Pending
3.2 | Results |  | 2026-10-19 | 2026-10-20 |  |  | 2
3.2.1 | Mutant sequence findings | Leyre | 2026-10-19 | 2026-10-20 |  |  | 2 | 2.1.3 | Pending
3.2.2 | Evolutionary findings | Noa | 2026-10-20 | 2026-10-20 |  |  | 1 | 2.2.3 | Pending
3.2.3 | Structure and functional impact findings | Ferran | 2026-10-20 | 2026-10-20 |  |  | 1 | 2.3.1 | Pending
3.3 | Discussion and Conclusions |  | 2026-10-21 | 2026-10-22 |  |  | 2
3.3.1 | Results interpretation | Noa | 2026-10-21 | 2026-10-21 |  |  | 1 | 3.2.1, 3.2.2, 3.2.3 | Pending
3.3.2 | Correlation with the disease | Luz | 2026-10-21 | 2026-10-21 |  |  | 1 | 2.3.2, 3.2.1, 3.2.2, 3.2.3 | Pending
3.3.3 | Conclusions | Luz | 2026-10-22 | 2026-10-22 |  |  | 1 | 3.3.1, 3.3.2 | Pending
3.4 | Integration and final review |  | 2026-10-21 | 2026-10-23 |  |  | 3
3.4.1 | Word-count and figure-limit check | Ferran | 2026-10-21 | 2026-10-21 |  |  | 1 | 3.2.1, 3.2.2, 3.2.3 | Pending
3.4.2 | Integration of sections, Abstract and Keywords | Noa | 2026-10-22 | 2026-10-22 |  |  | 1 | 3.1.3, 3.3.1, 3.3.2, 3.4.1 | Pending
3.4.3 | Reference and citation check | Luz | 2026-10-23 | 2026-10-23 |  |  | 1 | 1.3.3, 3.4.2 | Pending
3.4.4 | Grammar and style check | Ferran | 2026-10-23 | 2026-10-23 |  |  | 1 | 3.4.2 | Pending
3.4.5 | Rubric and delivery checklist, Authors' contributions | Luz | 2026-10-23 | 2026-10-23 |  |  | 1 | 3.3.3, 3.4.2 | Pending
4 | Oral presentation |  | 2026-10-27 | 2026-11-04 |  |  | 7
4.1 | Presentation preparation |  | 2026-10-27 | 2026-11-04 |  |  | 7
4.1.1 | Slide structure and template | Noa | 2026-10-27 | 2026-10-28 |  |  | 2 | 3.4.5 | Pending
4.1.2 | Slides for own section | All | 2026-10-29 | 2026-10-30 |  |  | 2 | 4.1.1 | Pending
4.1.3 | Cross-explanation session | All | 2026-11-02 | 2026-11-02 |  |  | 1 | 4.1.2 | Pending
4.1.4 | Rehearsal with questions | All | 2026-11-03 | 2026-11-04 |  |  | 2 | 4.1.3 | Pending
M | Milestones
M1 | Gantt v1 delivered (Moodle, 22:00) | — | 2026-10-09 | 2026-10-09 |  |  | 0 | 1.2.3 | Pending | bar: 2026-10-09
M2 | Variants and species selected | — | 2026-10-14 | 2026-10-14 |  |  | 0 | 2.1.2, 2.2.1 | Pending | bar: 2026-10-14
M3 | Analyses completed | — | 2026-10-20 | 2026-10-20 |  |  | 0 | 2.2.3, 2.3.2 | Pending | bar: 2026-10-20
M4 | Content freeze | — | 2026-10-21 | 2026-10-21 |  |  | 0 | 3.1.3, 3.3.1, 3.3.2 | Pending | bar: 2026-10-21
M5 | Status retrospective | — | 2026-10-22 | 2026-10-22 |  |  | 0 | 1.4.3 | Pending | bar: 2026-10-22
M6 | Final delivery (GitHub, 22:00) | — | 2026-10-26 | 2026-10-26 |  |  | 0 | 3.4.3, 3.4.4, 3.4.5 | Pending | bar: 2026-10-26
M7 | Oral presentation | — | 2026-11-05 | 2026-11-05 |  |  | 0 | 4.1.4 | Pending | bar: 2026-11-05
Legend
Completed — Task bar coloured by status (Status sheet)
In progress — Task bar coloured by status (Status sheet)
Incident — Task bar coloured by status (Status sheet)
Pending — Task bar coloured by status (Status sheet)
Canceled — Task bar coloured by status (Status sheet)
◆ Milestone — Checkpoint without duration
Holiday — Bank holiday (24/09 La Mercè, 12/10); weekends are not shown
Predecessors are finish-to-start unless marked (SS) = start-to-start.

## Status
Project Status — ALS1
Team: Ferran · Luz · Noa · Leyre ¦ Course: Introduction to Bioinformatics 2026–2027
Updated up to: |  | 2026-10-08 |  |  | Predecessors are finish-to-start unless marked (SS) = start-to-start (can start once the predecessor has started).
ID | Task | Owner | Output | Accomplished when | Predecessor | Plan. start | Plan. finish | Duration (working days) | Real start | Real finish | Status | Notes
1 | Project management & setup |  |  |  |  | 2026-09-17 | 2026-10-26 | 26
1.1 | GitHub environment setup |  |  |  |  | 2026-09-17 | 2026-10-09 | 16
1.1.1 | Setting up repository | Noa & Ferran | Shared GitHub repository with folder structure | All members are collaborators and can clone, commit and push |  | 2026-09-17 | 2026-09-17 | 1 | 2026-09-17 | 2026-09-17 | Completed | Repository created and folders added on 17/09
1.1.2 | Repository update to Formal Requirements (name, report/, references/, README) | Leyre | Repository compliant with Formal Requirements | Repo named NFL_ALS1_IB_2026; report/, status/, gantt/, references/ exist; README lists members, roles and structure | 1.1.1 | 2026-10-09 | 2026-10-09 | 1 |  |  | Pending | Remove unrelated entries (TTR, serum albumin) from the bibliography file
1.2 | Project planning |  |  |  |  | 2026-10-01 | 2026-10-09 | 7
1.2.1 | Gantt chart (Excel) | All | Gantt chart, task details and milestones | All tasks have owner, output, duration, predecessor and completion criteria | 1.1.1 | 2026-10-01 | 2026-10-08 | 6 | 2026-09-29 |  | In progress | First Excel version committed on 29/09
1.2.2 | Risk assessment | Leyre | Risk register and contingency plans | Each risk has score, category, contingency plan and owner; mandatory risk sentence written | 1.2.1 (SS) | 2026-10-05 | 2026-10-08 | 4 | 2026-10-06 |  | In progress
1.2.3 | Gantt v1 export to PDF, Moodle submission and freeze in repo | Luz | Gantt v1 PDF on Moodle and in gantt/ | PDF uploaded before 20:00 on 09/10 and committed to gantt/ | 1.2.1, 1.2.2 | 2026-10-09 | 2026-10-09 | 1 |  |  | Pending | Moodle deadline 22:00; upload at least 2 h earlier
1.3 | Literature review |  |  |  |  | 2026-10-06 | 2026-10-22 | 12
1.3.1 | Bibliography selection | All | List of relevant sources on ALS1 / SOD1 | Key reviews and database entries (OMIM, UniProt, ClinVar, PDB) identified |  | 2026-10-06 | 2026-10-09 | 4 | 2026-10-06 |  | In progress | Every member searches sources
1.3.2 | Extraction of information and storage of sources | All | Notes per topic; source PDFs in references/ | Each used source is stored in references/ (PDF preferred) | 1.3.1 | 2026-10-13 | 2026-10-21 | 7 |  |  | Pending
1.3.3 | In-text citations and reference list (Oxford SCIMED) | All | Citations in report.md and reference list | Every statement taken from a source is cited in Oxford SCIMED style | 1.3.1 | 2026-10-15 | 2026-10-22 | 6 |  |  | Pending | Done while writing each section
1.4 | Project monitoring |  |  |  |  | 2026-10-09 | 2026-10-26 | 11
1.4.1 | Project Status and live Gantt updates (Mon & Thu) | Ferran | Updated Status sheet, live Gantt and status/project_status.md | Real dates, status and notes updated every Monday and Thursday | 1.2.1 | 2026-10-09 | 2026-10-26 | 11 |  |  | Pending | Final Gantt must reflect real progress on 26/10
1.4.2 | Risk monitoring | Leyre | Updated risk register | Score and status of each risk reviewed every week; activated contingencies recorded | 1.2.2 | 2026-10-09 | 2026-10-26 | 11 |  |  | Pending
1.4.3 | Retrospective preparation | Ferran | Status summary for the 22/10 retrospective | Delays, incidents and decisions documented in Notes | 1.4.1 (SS) | 2026-10-21 | 2026-10-21 | 1 |  |  | Pending
2 | Bioinformatic analysis |  |  |  |  | 2026-10-13 | 2026-10-20 | 6
2.1 | Sequence, mutation and structure analysis |  |  |  |  | 2026-10-13 | 2026-10-16 | 4
2.1.1 | Disease cause at gene, protein, structure and function level | Luz | Summary of SOD1 gene, protein, structure and function in ALS1 | Cause of ALS1 explained at the four levels with sources | 1.3.1 | 2026-10-13 | 2026-10-14 | 2 |  |  | Pending
2.1.2 | Variant selection and numbering mapping table | Leyre | 2–3 selected variants + legacy ↔ HGVS mapping table | Variants chosen with explicit criteria (ClinVar classification, literature, structure availability); one numbering convention fixed | 1.3.1 | 2026-10-13 | 2026-10-14 | 2 |  |  | Pending | Contingency for risks 'too much information' and 'source mismatch'
2.1.3 | Wild-type vs mutant sequence alignment | Leyre | Pairwise alignments and interpretation | Each selected variant located and described in the alignment | 2.1.2 | 2026-10-15 | 2026-10-16 | 2 |  |  | Pending
2.1.4 | Mapping of variants onto the 3D structure | Ferran | Structure figures with mutated residues highlighted | Each variant mapped onto the SOD1 structure (PDB) with its structural context | 2.1.2 | 2026-10-15 | 2026-10-16 | 2 |  |  | Pending
2.2 | Evolutionary conservation |  |  |  |  | 2026-10-13 | 2026-10-19 | 5
2.2.1 | Species selection (≥ 2) and ortholog retrieval | Noa | Justified species list and SOD1 ortholog sequences | At least 2 species selected and justified; orthologs (not paralogs) retrieved | 1.3.1 | 2026-10-13 | 2026-10-14 | 2 |  |  | Pending | Bos taurus proposed: check its SOD1 UniProt entry (current link O46375 seems to be TTR)
2.2.2 | Multiple sequence alignment and conservation of mutated residues | Noa | MSA and conservation analysis | Conservation of each selected residue described across species | 2.1.2, 2.2.1 | 2026-10-15 | 2026-10-16 | 2 |  |  | Pending
2.2.3 | Selective pressure in evolution | Noa | Interpretation of evolutionary constraint | Biological implication of conservation explained | 2.2.2 | 2026-10-19 | 2026-10-19 | 1 |  |  | Pending
2.3 | Structure–function impact |  |  |  |  | 2026-10-19 | 2026-10-20 | 2
2.3.1 | Healthy vs disease differences at gene, protein, structure and function level | Ferran | Comparison table healthy vs disease | Differences described at the four levels for each variant | 2.1.1, 2.1.3, 2.1.4 | 2026-10-19 | 2026-10-19 | 1 |  |  | Pending
2.3.2 | Impact on patient function | Luz | Explanation of the physiological consequences | Link between molecular change and clinical phenotype explained with sources | 2.3.1 | 2026-10-20 | 2026-10-20 | 1 |  |  | Pending
3 | Report writing (BMC Bioinformatics format) |  |  |  |  | 2026-10-13 | 2026-10-23 | 9
3.1 | Background and Methods |  |  |  |  | 2026-10-13 | 2026-10-21 | 7
3.1.1 | Report skeleton (BMC sections) and figure plan | Ferran | report/report.md skeleton and list of max. 5 figures/tables | All BMC sections present with owner and word budget | 1.1.2 | 2026-10-13 | 2026-10-13 | 1 |  |  | Pending
3.1.2 | Background | Luz | Background section | Disease context, aims and research gap written and cited | 2.1.1, 3.1.1 | 2026-10-15 | 2026-10-16 | 2 |  |  | Pending
3.1.3 | Methods | Leyre | Methods section | Data sources, tools, versions and numbering convention described for reproducibility | 2.1.3, 2.1.4, 2.2.2 | 2026-10-21 | 2026-10-21 | 1 |  |  | Pending
3.2 | Results |  |  |  |  | 2026-10-19 | 2026-10-20 | 2
3.2.1 | Mutant sequence findings | Leyre | Results subsection | Sequence findings written with figures/tables referenced | 2.1.3 | 2026-10-19 | 2026-10-20 | 2 |  |  | Pending
3.2.2 | Evolutionary findings | Noa | Results subsection | Conservation findings written with figures/tables referenced | 2.2.3 | 2026-10-20 | 2026-10-20 | 1 |  |  | Pending
3.2.3 | Structure and functional impact findings | Ferran | Results subsection | Structural findings written with figures/tables referenced | 2.3.1 | 2026-10-20 | 2026-10-20 | 1 |  |  | Pending
3.3 | Discussion and Conclusions |  |  |  |  | 2026-10-21 | 2026-10-22 | 2
3.3.1 | Results interpretation | Noa | Discussion subsection | Findings compared with literature; limitations stated | 3.2.1, 3.2.2, 3.2.3 | 2026-10-21 | 2026-10-21 | 1 |  |  | Pending
3.3.2 | Correlation with the disease | Luz | Discussion subsection | Molecular findings linked to the ALS1 phenotype | 2.3.2, 3.2.1, 3.2.2, 3.2.3 | 2026-10-21 | 2026-10-21 | 1 |  |  | Pending
3.3.3 | Conclusions | Luz | Conclusions section | Main conclusions answer the project question | 3.3.1, 3.3.2 | 2026-10-22 | 2026-10-22 | 1 |  |  | Pending | Synthesis only: no new analyses after the 21/10 content freeze
3.4 | Integration and final review |  |  |  |  | 2026-10-21 | 2026-10-23 | 3
3.4.1 | Word-count and figure-limit check | Ferran | Checked draft | ≤ 5000 words / 7 pages and ≤ 5 figures/tables | 3.2.1, 3.2.2, 3.2.3 | 2026-10-21 | 2026-10-21 | 1 |  |  | Pending | Contingency of the format risk (check on 21/10)
3.4.2 | Integration of sections, Abstract and Keywords | Noa | Complete integrated report.md | Sections connected; structured Abstract ≤ 350 words; 5 keywords | 3.1.3, 3.3.1, 3.3.2, 3.4.1 | 2026-10-22 | 2026-10-22 | 1 |  |  | Pending | Synthesis only: no new analyses after the 21/10 content freeze
3.4.3 | Reference and citation check | Luz | Verified reference list | All citations match the list and the PDFs in references/ | 1.3.3, 3.4.2 | 2026-10-23 | 2026-10-23 | 1 |  |  | Pending
3.4.4 | Grammar and style check | Ferran | Proofread report | UK spelling (-ize), Oxford comma and number style applied | 3.4.2 | 2026-10-23 | 2026-10-23 | 1 |  |  | Pending
3.4.5 | Rubric and delivery checklist, Authors' contributions | Luz | Completed checklist and Declarations | All Formal Requirements and rubric items checked; contributions stated | 3.3.3, 3.4.2 | 2026-10-23 | 2026-10-23 | 1 |  |  | Pending | 26/10 kept as buffer only (no new tasks)
4 | Oral presentation |  |  |  |  | 2026-10-27 | 2026-11-04 | 7
4.1 | Presentation preparation |  |  |  |  | 2026-10-27 | 2026-11-04 | 7
4.1.1 | Slide structure and template | Noa | Slide template and outline | Outline agreed by the team | 3.4.5 | 2026-10-27 | 2026-10-28 | 2 |  |  | Pending | After final delivery; nothing committed after 26/10 22:00
4.1.2 | Slides for own section | All | Complete slide deck | Each member's slides added to the deck | 4.1.1 | 2026-10-29 | 2026-10-30 | 2 |  |  | Pending | Each member prepares the part they present
4.1.3 | Cross-explanation session | All | Shared understanding of all sections | Each member can explain every section (risk: niche awareness) | 4.1.2 | 2026-11-02 | 2026-11-02 | 1 |  |  | Pending
4.1.4 | Rehearsal with questions | All | Rehearsed presentation | Full run within time; questions on other members' sections answered | 4.1.3 | 2026-11-03 | 2026-11-04 | 2 |  |  | Pending
M | Milestones
M1 | Gantt v1 delivered (Moodle, 22:00) | — |  |  | 1.2.3 | 2026-10-09 | 2026-10-09 | 0 |  |  | Pending
M2 | Variants and species selected | — |  |  | 2.1.2, 2.2.1 | 2026-10-14 | 2026-10-14 | 0 |  |  | Pending
M3 | Analyses completed | — |  |  | 2.2.3, 2.3.2 | 2026-10-20 | 2026-10-20 | 0 |  |  | Pending
M4 | Content freeze | — |  |  | 3.1.3, 3.3.1, 3.3.2 | 2026-10-21 | 2026-10-21 | 0 |  |  | Pending
M5 | Status retrospective | — |  |  | 1.4.3 | 2026-10-22 | 2026-10-22 | 0 |  |  | Pending
M6 | Final delivery (GitHub, 22:00) | — |  |  | 3.4.3, 3.4.4, 3.4.5 | 2026-10-26 | 2026-10-26 | 0 |  |  | Pending | Last commit before 22:00; later commits are discarded
M7 | Oral presentation | — |  |  | 4.1.4 | 2026-11-05 | 2026-11-05 | 0 |  |  | Pending
Formulas:
Plan. start = MIN([Plan. start, row below]:G20)
Plan. finish = MAX([Plan. finish, row below]:H20)
Duration (working days) = IF(OR([Plan. start]="",[Plan. finish]=""),"",NETWORKDAYS([Plan. start],[Plan. finish],{46289;46307}))

## Risks
Risk management — ALS1
Team: Ferran · Luz · Noa · Leyre ¦ Course: Introduction to Bioinformatics 2026–2027
ID | Risk | Type | L | I | S | Category | We have realized because… | Contingency plan | Related task | Owner | Status
R1 | Using terms we don't understand or including GenAI errors or hallucinations | Scientific | 2 | 3 | 6 | High | SOD1 literature uses highly specialised terminology and the IB GenAI policy makes us liable for any GenAI-generated content. | Each section is cross-read by the other members, who must be able to understand and explain it. GenAI is only used for wording and formatting, outside GitHub, and its output is always checked manually. | 3.4.3 | Luz | Open
R2 | Tight schedule: deadline | Team & planning | 2 | 3 | 6 | High | The final deadline on Moodle is Monday 26/10 at 22:00, and only two working days remain after the 22/10 retrospective. | Content freeze on 21/10; 22–23/10 for integration and review only; 26/10 kept exclusively as a buffer. | 1.4.1 | Ferran | Open
R3 | Uneven contribution | Team & planning | 2 | 3 | 6 | High | Our first Gantt draft assigned several tasks to "All" | Every task has a single owner and a balanced workload; each member commits their own work at least twice a week. Tasks are reassigned early if someone falls behind. | 1.4.1 | Ferran | Open
R4 | "Niche awareness" at the oral presentation | Team & planning | 2 | 3 | 6 | High | Our analysis tasks are split by specialisation, each owned by a single member, while the rubric assesses every member's understanding of the whole project. | Short weekly sync where each member explains their progress to the rest; each section is cross-read by a different member; everyone reads the full report before the presentation; a rehearsal with questions about other members' sections. | 4.1.1 | Noa | Open
R5 | Mismatch between different sources leads to wrong positions in alignments and structures | Scientific | 3 | 2 | 6 | High | The same SOD1 mutation is named A4V in the classic literature but p.Ala5Val in ClinVar. | Before any analysis, define a single numbering convention in Methods and build a mapping table between sources. | 2.1.2 | Leyre | Open
R6 | Trying to analyse too much information (e.g. too many variants) | Scientific | 3 | 2 | 6 | High | ClinVar currently lists 194 SOD1 variants classified as pathogenic or likely pathogenic (consulted 08/10), far more than we can analyse. | Select 2–3 representative variants using explicit criteria by a fixed date (14/10); anything outside that scope is left for the Discussion as future work. | 2.1.2 | Leyre | Open
R7 | Format errors in the submissions | Technical & format | 2 | 2 | 4 | Medium | The Formal Requirements and the BMC template impose many formal rules. | Build a checklist from the Formal Requirements and the BMC template (repo name, mandatory folders, .md report, word limits…) and review it before each delivery. Agree an approximate word budget per section from the start. Check the word count on 21/10. | 3.4.5 | Luz | Open
R8 | Technical problems with Git files or GitHub | Technical & format | 2 | 2 | 4 | Medium | Several attempts to fix the folder structure. | Small and frequent commits. Upload deliverables at least 2 h before the deadline. | 1.1.2 | Leyre | Open
R9 | Gantt and Status not kept up to date | Team & planning | 2 | 2 | 4 | Medium | Our first versions of the Gantt and of the Project Status had empty fields and outdated dates. | One owner updates the Project Status and the live Gantt every Monday and Thursday with real dates, status and notes; each member reports their progress at each meeting. | 1.4.1 | Ferran | Open
R10 | Distant species make the comparison hard to interpret | Scientific | 1 | 2 | 2 | Low | The project requires comparing human SOD1 with at least two other species, and the candidates range from close mammals to very distant organisms with much less similar sequences. | Choose species with a clear biological or experimental justification. If the distant species alignment is not informative, replace it with an intermediate one and explain the choice in Methods. | 2.2.1 | Noa | Open
R11 | Online tools unavailable or slow close to the deadline | Technical & format | 1 | 2 | 2 | Low | The tools we need (BLAST, multiple sequence alignment servers) are shared public services with job queues, used by all groups in the same weeks. | Run all analyses early, well before the content freeze; save every output (files + screenshots, with date and tool version). | 2.2.2 | Noa | Open